## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Course -> getExamDate() | Get exam_date for a course gives an error | Critical | 10 | 111 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 1 | Authentication | Undefined variable: studentDao; wrong variable name | Critical | 10
3 | 1 | Authentication | token generated for a wrong pair of userid and password | Critical | 10
4 | 1 | Authentication | error message for correct pairs of userid and password | Critical | 10
5 | 1 | Authentication | error message not following the desired format | low | 1
6 | 1 | Student->setEdollar() | Undefined variable: edollar; did not specify parameters in the setEdollar function | Critical | 10
7 | 1 | BidDAO()->retrieveAll() & retrieveBid() & addBid() | misspelled function names | Critical | 10
8 | 1 | BidDAO() functions | wrong column specified in the sql statement | Critical | 10
9 | 1 | CourseDAO()->retrieveAll() | misspelled function names; wrong key to associative array | Critical | 10
10 | 1 | EnrolmentDAO() functions | wrong column specified in the sql statement | Critical | 10
11 | 1 | Bootstrap | system shows error messages | High | 5
12 | 1 | Bootstrap | When submitting missing csv zip file after one round of successful bootstrap, the bootstrap function still works | High | 5
13 | 1 | Bootstrap | section is validated even when the course is invalid | High | 5
14 | 1 | Bootstrap | section is validated wrongly even when the section id is valid | High | 5
15 | 1 | Bootstrap | round 1 not automatically started after successful boostrap | High | 5 | 89 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
16 | 2 | protect | students who login are not redirected back to student-home.php if directly access admin-home.php | High | 5
17 | 2 | bid-section | students bid a section that he has bidded before will run into errors | Critical | 10
18 | 2 | user-dump | edollar balance of the student is shown as an integer when the value is a whole number | low | 1
19 | 2 | section-dump | amount of the bid is shown as an integer when the value is a whole number | low | 1
20 | 2 | bid-dump | amount of the bid is shown as an integer when the value is a whole number | low | 1
21 | 2 | delete-bid | run into error as function parameters are not updated | Critical | 10
22 | 2 | update-bid | run into error as function parameters are not updated | Critical | 10
23 | 2 | bootstrap | students' edollars are not deducted by the bid amount | High | 5
24 | 2 | Bootstrap | the bid is not updated when there is a new row of the student bidding the same course, instead that row will fail | Critical | 10
25 | 2 | update-bid | when it is a new bid, it is not added to the bid database but shows error | Critical | 10
26 | 2 | section-dump | the error from common validation is not sorted by field name | low | 1
27 | 2 | update-bid | when student bid the same course, the programme shows bid exists | Critical | 10
28 | 2 | update-bid | common validation for userid and amount are not checked | Critical | 10
29 | 3 | drop-section | when a student drops a section, the vacancy information is not updated in round_clear table | High | 5 | 41 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
30 | 3 | admin-home | the round status is not displayed before bootstrap | low | 1
31 | 3 | bid section | when a student has enrolled in courses, he can still have 5 bids | high | 5
32 | 3 | bootstrap | the errors are not sorted by file and line number | high | 5
33 | 3 | update real time bid information | when a user updates his bid equal to the min_bid, the status are wrong | High | 5
34 | 3 | update-bid | can only update bid amount but not section id | high | 5
35 | 3 | dump | section-student is not sorted as required | high | 5
36 | 3 | dump | the day information is wrong | high | 5
37 | 4 | Bootstrap | number of lines loaded are not in separate arrays | High | 5
38 | 4 | bid-section | clashing class time table and exam time table is not captured | High | 5 | 78 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
39 | 4 | stop round | Bid table is not cleared when admin end rounds through UI causing errors | High | 5
40 | 4 | bid-section | when end time = start time for lesson and exam, it shows clashing | high | 5
41 | 4 | Bootstrap | line number starts at 1 for first row of records | low | 1
42 | 4 | delete-bid | round ended error is not shown when there is invalid inputs | High | 5
43 | 4 | update-bid | round ended error is not shown when there is invalid inputs | High | 5
44 | 4 | drop-section | round not active error is not shown when there is invalid inputs | High | 5
45 | 4 | dump | float values are not in 2dp | low | 1
46 | 4 | authenticate | password and username error are not sorted by field name | low | 1
47 | 4 | bootstrap | The added bid is dropped when the new row of bid is invalid | Critical | 10
48 | 4 | dump | school information of the course is not shown | High | 5
49 | 4 | stop | the vacancy is negative | Critical | 10
50 | 4 | Bootstrap & bid-section | clashing class time table and exam time table is wrong in logic; enrolled courses' timetables are not checked | Critical | 10
51 | 4 | bootstrap | section validation fails to capture errors like S01 | Critical | 10
52 | 5 | bid-status | status values are captialized | High | 5 | 25 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
53 | 5 | bid-status | min bid is not following the logic | Critical | 10
54 | 5 | delete-bid | the function shows successful deletion of a student's bid of the same course but different section | High | 5
55 | 5 | bootstrap | invalid end wrong logic | High | 5
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team) | 2019-09-21 | 2019-09-29 | 2019-10-05 | 2019-10-12 | 2019-10-13 | 2019-10-16 | 2019-10-21 | 2019-10-24 | 2019-10-28 | 2019-11-01 | 2019-11-06 | 2019-11-08 | 2019-11-17
1 | 1 | Course -> getExamDate() | Get exam_date for a course gives an error | Resolved | 2019-09-21 | 2019-09-21 | QH & NG | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
2 | 1 | Authentication | Undefined variable: studentDao; wrong variable name | Resolved | 2019-09-21 | 2019-09-21 | QH & NG | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
3 | 1 | Authentication | token generated for a wrong pair of userid and password | Resolved | 2019-09-21 | 2019-09-21 | QH & NG | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
4 | 1 | Authentication | error message for correct pairs of userid and password | Resolved | 2019-09-21 | 2019-09-21 | QH & NG | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
5 | 1 | Authentication | error message not following the desired format | Resolved | 2019-09-21 | 2019-09-21 | QH & NG | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
6 | 1 | Student->setEdollar() | Undefined variable: edollar; did not specify parameters in the setEdollar function | Resolved | 2019-09-21 | 2019-09-21 | EY & SYR | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
7 | 1 | BidDAO()->retrieveAll() & retrieveBid() & addBid() | misspelled function names | Resolved | 2019-09-21 | 2019-09-21 | QH & NG | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
8 | 1 | BidDAO() functions | wrong column specified in the sql statement | Resolved | 2019-09-21 | 2019-09-21 | QH & NG | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
9 | 1 | CourseDAO()->retrieveAll() | misspelled function names; wrong key to associative array | Resolved | 2019-09-21 | 2019-09-21 | EY & SYR | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
10 | 1 | EnrolmentDAO() functions | wrong column specified in the sql statement | Resolved | 2019-09-21 | 2019-09-21 | EY & SYR | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
11 | 1 | Bootstrap | system shows error messages | Resolved | 2019-09-29 | 2019-09-29 | QH & NG |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
12 | 1 | Bootstrap | When submitting missing csv zip file after one round of successful bootstrap, the bootstrap function still works | Resolved | 2019-09-29 | 2019-09-29 | QH & NG |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
13 | 1 | Bootstrap | section is validated even when the course is invalid | Resolved | 2019-09-29 | 2019-09-29 | QH & NG |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
14 | 1 | Bootstrap | section is validated wrongly even when the section id is valid | Resolved | 2019-09-29 | 2019-09-29 | QH & NG |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
15 | 1 | Bootstrap | round 1 not automatically started after successful boostrap | Resolved | 2019-09-29 | 2019-09-29 | QH & NG |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
16 | 2 | protect | students who login are not redirected back to student-home.php if directly access admin-home.php | Resolved | 2019-10-05 | 2019-10-05 | QH & NG |  |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
17 | 2 | bid-section | students bid a section that he has bidded before will run into errors | Resolved | 2019-10-05 | 2019-10-05 | QH & NG |  |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
18 | 2 | user-dump | edollar balance of the student is shown as an integer when the value is a whole number | Resolved | 2019-10-12 | 2019-10-12 | QH&EY |  |  |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
19 | 2 | section-dump | amount of the bid is shown as an integer when the value is a whole number | Resolved | 2019-10-12 | 2019-10-12 | QH&EY |  |  |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
20 | 2 | bid-dump | amount of the bid is shown as an integer when the value is a whole number | Resolved | 2019-10-12 | 2019-10-12 | QH&EY |  |  |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
21 | 2 | delete-bid | run into error as function parameters are not updated | Resolved | 2019-10-12 | 2019-10-12 | NG & YR |  |  |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
22 | 2 | update-bid | run into error as function parameters are not updated | Resolved | 2019-10-12 | 2019-10-12 | QH&EY |  |  |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
23 | 2 | bootstrap | students' edollars are not deducted by the bid amount | Resolved | 2019-10-12 | 2019-10-12 | QH&EY |  |  |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
24 | 2 | Bootstrap | the bid is not updated when there is a new row of the student bidding the same course, instead that row will fail | Resolved | 2019-10-12 | 2019-10-12 | QH&EY |  |  |  | pass | pass | pass | pass | pass | pass | pass | pass | pass | pass
25 | 2 | update-bid | when it is a new bid, it is not added to the bid database but shows error | Resolved | 2019-10-13 | 2019-10-13 | QH&EY |  |  |  |  | pass | pass | pass | pass | pass | pass | pass | pass | pass
26 | 2 | section-dump | the error from common validation is not sorted by field name | Resolved | 2019-10-13 | 2019-10-13 | QH&EY |  |  |  |  | pass | pass | pass | pass | pass | pass | pass | pass | pass
27 | 2 | update-bid | when student bid the same course, the programme shows bid exists | Resolved | 2019-10-13 | 2019-10-13 | QH&EY |  |  |  |  | pass | pass | pass | pass | pass | pass | pass | pass | pass
28 | 2 | update-bid | common validation for userid and amount are not checked | Resolved | 2019-10-13 | 2019-10-13 | QH&EY |  |  |  |  | pass | pass | pass | pass | pass | pass | pass | pass | pass
29 | 3 | drop-section | when a student drops a section, the vacancy information is not updated in round_clear table | Resolved | 2019-10-16 | 2019-10-16 | QH&SYK | [5 empty] | pass | pass | pass | pass | pass | pass | pass | pass
30 | 3 | admin-home | the round status is not displayed before bootstrap | Resolved | 2019-10-16 | 2019-10-21 | QH&SYK | 2019-10-21: pass; 2019-10-24: pass; 2019-10-28: pass; 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
31 | 3 | bid section | when a student has enrolled in courses, he can still have 5 bids | Resolved | 2019-10-16 | 2019-10-21 | QH&SYK | 2019-10-21: pass; 2019-10-24: pass; 2019-10-28: pass; 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
32 | 3 | bootstrap | the errors are not sorted by file and line number | Resolved | 2019-10-21 | 2019-10-21 | EY & SYR | 2019-10-21: pass; 2019-10-24: pass; 2019-10-28: pass; 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
33 | 3 | update real time bid information | when a user updates his bid equal to the min_bid, the status are wrong | Resolved | 2019-10-24 | 2019-10-24 | QH & SYK | 2019-10-24: pass; 2019-10-28: pass; 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
34 | 3 | update-bid | can only update bid amount but not section id | Resolved | 2019-10-24 | 2019-10-24 | QH & SYK | 2019-10-24: pass; 2019-10-28: pass; 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
35 | 3 | dump | section-student is not sorted as required | Resolved | 2019-10-24 | 2019-10-24 | EY & SYR | 2019-10-24: pass; 2019-10-28: pass; 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
36 | 3 | dump | the day information is wrong | Resolved | 2019-10-24 | 2019-10-24 | QH & SYK | 2019-10-24: pass; 2019-10-28: pass; 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
37 | 4 | Bootstrap | number of lines loaded are not in separate arrays | Resolved | 2019-10-29 | 2019-11-01 | EY & SYR | 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
38 | 4 | bid-section | clashing class time table and exam time table is not captured | Resolved | 2019-10-29 | 2019-11-01 | NG & SY | 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
39 | 4 | stop round | Bid table is not cleared when admin end rounds through UI causing errors | Resolved | 2019-10-29 | 2019-11-01 | EY & SYR | 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
40 | 4 | bid-section | when end time = start time for lesson and exam, it shows clashing | Resolved | 2019-10-29 | 2019-11-01 | QH&SYR | 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
41 | 4 | Bootstrap | line number starts at 1 for first row of records | Resolved | 2019-10-29 | 2019-11-01 | EY & SYR | 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
42 | 4 | delete-bid | round ended error is not shown when there is invalid inputs | Resolved | 2019-10-29 | 2019-11-01 | NG & SY | 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
43 | 4 | update-bid | round ended error is not shown when there is invalid inputs | Resolved | 2019-10-31 | 2019-11-01 | NG & SY | 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
44 | 4 | drop-section | round not active error is not shown when there is invalid inputs | Resolved | 2019-10-31 | 2019-11-01 | NG & SY | 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
45 | 4 | dump | float values are not in 2dp | Resolved | 2019-10-31 | 2019-11-01 | QH&SYR | 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
46 | 4 | authenticate | password and username error are not sorted by field name | Resolved | 2019-10-31 | 2019-11-01 | QH&SYR | 2019-11-01: pass; 2019-11-06: pass; 2019-11-08: pass; 2019-11-17: pass
47 | 4 | bootstrap | The added bid is dropped when the new row of bid is invalid | Resolved | 2019-11-07 | 2019-11-07 | NG & SY | 2019-11-08: pass; 2019-11-17: pass
48 | 4 | dump | school information of the course is not shown | Resolved | 2019-11-07 | 2019-11-07 | NG & SY | 2019-11-08: pass; 2019-11-17: pass
49 | 4 | stop | the vacancy is negative | Resolved | 2019-11-07 | 2019-11-07 | NG & SY | 2019-11-08: pass; 2019-11-17: pass
50 | 4 | Bootstrap & bid-section | clashing class time table and exam time table is wrong in logic; enrolled courses' timetables are not checked | Resolved | 2019-11-07 | 2019-11-08 | SY & NG | 2019-11-08: pass; 2019-11-17: pass
51 | 4 | bootstrap | section validation fails to capture errors like S01 | Resolved | 2019-11-07 | 2019-11-08 | SY & NG | 2019-11-08: pass; 2019-11-17: pass
52 | 5 | bid-status | status values are captialized | Resolved | 2019-11-17 | 2019-11-17 | SYR & NG | 2019-11-17: pass
53 | 5 | bid-status | min bid is not following the logic | Resolved | 2019-11-17 | 2019-11-17 | SYR & NG | 2019-11-17: pass
54 | 5 | delete-bid | the function shows successful deletion of a student's bid of the same course but different section | Resolved | 2019-11-17 | 2019-11-17 | SYR & NG | 2019-11-17: pass
55 | 5 | bootstrap | invalid end wrong logic | Resolved | 2019-11-17 | 2019-11-17 | SYR & NG | 2019-11-17: pass