## Week 13
Soo Yeon | Question | Week: 30/9/2019 to 6/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Nanda | What did you do yesterday? | not a working day | read wiki for final presentation | not a working day | generate some test cases | consolidate test cases and meet for final presentations | not working day | tidy up manual test cases
| What will you do today? | Read wiki | not a working day | generate some test cases | consolidate test cases and meet for final presentations | not working day | tidy up manual test cases | meet for final submission and deployment
| Do you have any obstacles? | nil | nil | nil | nil | nil | nil | confusion about test plan
Soo Yeon | What did you do yesterday? | not a working day | Read wiki | read codes and ask YR | not a working day | meet for final presentation | not working day | create more json checker test cases
| What will you work on today? | Read wiki | read codes | not a working day | meet for final presentation | not working day | create more json checker test cases | meet for final submission and deployment
| Do you have any obstacles? | nil | nil | some questions in the logic of round clearing | nil | nil | nil | putting timeline into 2 slides
Ethan | What did you do yesterday? | not a working day | read wiki | go through codes with Haodi | not a working day | meet for final presentation | not working day | tidy up minutes
| What will you work on today? | Read wiki | go through codes with Haodi | not a working day | meet for final presentation | not working day | tidy up minutes | meet for final submission and deployment
| Do you have any obstacles? | nil | do not know some functions in json checker | nil | nil | nil | nil | nil
Yan Rui | What did you do yesterday? | not a working day | read wiki | answered some questions from SY | generate some test cases | meet for final presentation | not working day | tidy up json checker test cases excel
| What will you work on today? | Read wiki | not a working day | generate some test cases | meet for final presentation | not working day | tidy up json checker test cases excel | meet for final submission and deployment
| Do you have any obstacles? | nil | nil | nil | nil | nil | nil | confusion about test plan
Haodi | What did you do yesterday? | not a working day | read wiki for final presentation | go through codes with Ethan | not a working day | meet for final presentation | not working day | tidy up bug metric and schedule
| What will you work on today? | Read wiki | go through codes with Ethan | not a working day | meet for final presentation | not working day | tidy up bug metric and schedule | meet for final submission and deployment
| Do you have any obstacles? | nil | nil | nil | nil | nil | nil | confusion about test plan

## Week 12
Person | Question | Week: 4/11/2019 - 10/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Nanda | What did you do yesterday? | not working day | not a working day | read the test cases | did not manage to debug | debugging with Soo yeon | debugging | not a working day
| What will you do today? | not working day | read the test cases | debugging with Soo Yeon | deugging with Soo Yeon | debugging | not a working day | not a working day
| Do you have any obstacles? | nil | nil | nil | nil | nil | nil | nil
Soo Yeon | What did you do yesterday? | not working day | not a working day | read the json checker | did not manage to debug | debugging with Soo yeon | debugging | not a working day
| What will you work on today? | not working day | read the json checker | debugging with Nanda | deugging with Nanda | debugging | not a working day | not a working day
| Do you have any obstacles? | nil | nil | nil | nil | nil | nil | nil
Ethan | What did you do yesterday? | not working day | not a working day | read through the codes | not a working day | read wiki | debugging | not a working day
| What will you work on today? | not working day | read through the codes | not a working day | Read wiki | debugging | not a working day | not a working day
| Do you have any obstacles? | nil | nil | nil | nil | nil | nil | nil
Yan Rui | What did you do yesterday? | not working day | not a working day | debug | not a working day | met haodi to discuss what to do | debugging | not a working day
| What will you work on today? | not working day | debug | not a working day | Meet haodi to discuss what to do | debugging | not a working day | not a working day
| Do you have any obstacles? | nil | nil | nil | nil | nil | nil | nil
Haodi | What did you do yesterday? | not working day | not a working day | debug | not a working day | met Yan ruito discuss what to do | debugging | not a working day
| What will you work on today? | not working day | debug | not a working day | Meet Yan Rui to discuss what to do | debugging | not a working day | not a working day
| Do you have any obstacles? | nil | nil | nil | nil | nil | nil | nil

## Week 11
Person | Question | Week: 28/10/2019 - 3/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | s
Nanda | What did you do yesterday? | Not working | Come out with test cases with Ethan for bid status | Not a working day | Test UI and see where can be improved | debugging | debugging | prep for UAT
| What will you do today? | Come out with test cases with Ethan for bid status | Not a working day | Test UI and see where UI can be improved | Debugging | debugging | Prep for UAT | not working day
| Do you have any obstacles? | Understanding how json checking work | nil | nil | nil | nil | nil | nil
Soo Yeon | What did you do yesterday? | Not working | Group meeting for UAT | Not a working day | Test UI and see where can be improved | debugging | debugging | prep for UAT
| What will you work on today? | Group meeting for UAT | Not a working day | Test UI and see where UI can be improved | Debugging | debugging | Prep for UAT | not working day
| Do you have any obstacles? | nil | nil | nil | nil | nil | nil | nil
Ethan | What did you do yesterday? | Not working day | Come out with test cases with Nanda for bid status | Not a working day | Read wiki to see if there is any new updates | debugging | debugging | prep for UAT
| What will you work on today? | Come out with test cases with Nanda for bid status | Not a working day | Read wiki to see if there is any new updates | Debugging | debugging | Prep for UAT | not working day
| Do you have any obstacles? | Understanding how Json Checking works | nil | nil | nil | nil | nil | nil
Yan Rui | What did you do yesterday? | Not working day | Come out with test cases with Nanda for bid status | Not a working day | Do json checking to see pass of fail | debugging | debugging | prep for UAT
| What will you work on today? | Group meeting for UAT | Not a working day | Do Json checking to see if they pass or fail | Debugging | debugging | Prep for UAT | not working day
| Do you have any obstacles? | nil | nil | nil | nil | nil | nil | nil
Haodi | What did you do yesterday? | Not working day | Group meeting for UAT | Not a working day | Check codes for bugs | debugging | debugging | prep for UAT
| What will you work on today? | Group meeting for UAT | not a working day | Check Codes if there are any bugs in code | Debugging | debugging | Prep for UAT | not working day
| Do you have any obstacles? | nil | nil | nil | nil | nil | nil | nil

## Week 10
Person | Question | Week: 21/10/2019 - 27/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Nanda | What did you do yesterday? | not a working day | group meeting for code testing | not a working day | not a working day | group meeting to test all codes | read codes and wiki page | not a working day
| What will you do today? | group meeting for code testing | not a working day | not a working day | group meeting to test all codes | read codes and wiki page | not a working day | not a working day
| Do you have any obstacles? | nil | nil | nil | none | none | nil | nil
Soo Yeon | What did you do yesterday? | not a working day | group meeting for code testing | not a working day | not a working day | group meeting to test all codes | not a working day | not a working day
| What will you work on today? | group meeting for code testing | not a working day | not a working day | group meeting to test all codes | not a working day | not a working day | not a working day
| Do you have any obstacles? | nil | nil | nil | none | nil | nil | nil
Ethan | What did you do yesterday? | not a working day | group meeting for code testing | not a working day | not a working day | group meeting to test all codes | not a working day | not a working day
| What will you work on today? | group meeting for code testing | not a working day | not a working day | group meeting to test all codes | not a working day | not a working day | not a working day
| Do you have any obstacles? | nil | nil | nil | none | nil | nil | nil
Yan Rui | What did you do yesterday? | not a working day | group meeting for code testing | not a working day | not a working day | group meeting to test all codes | not a working day | not a working day
| What will you work on today? | group meeting for code testing | not a working day | not a working day | group meeting to test all codes | not a working day | not a working day | not a working day
| Do you have any obstacles? | nil | nil | nil | none | nil | nil | nil
Haodi | What did you do yesterday? | not a working day | group meeting for code testing | not a working day | not a working day | group meeting to test all codes | not a working day | not a working day
| What will you work on today? | group meeting for code testing | not a working day | not a working day | group meeting to test all codes | not a working day | not a working day | not a working day
| Do you have any obstacles? | nil | nil | nil | none | nil | nil | nil

## Week 9
Person | Question | Week: 14/10/2019 - 20/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Nanda | What did you do yesterday? | Not a working day | Team meeting to discuss about schedule and update it | not a working day | Pair coding with ethan | not a working day | read round 2 clearing logic | not a working day
| What will you do today? | Team meeting to discuss about schedule and update it | Not a working day | pair coding with ethan | Not a working day | read round 2 clearing logic | not a working day | not a working day
| Do you have any obstacles? | None | None | nil | Nil | nil | nil | nil
Soo Yeon | What did you do yesterday? | Not a working day | discuss iter 3 scheduling | not a working day | Pair coding with haodi | not a working day | understand the code | not a working day
| What will you work on today? | Discuss iter 3 scheduling | not a working day | pair coding with haodi | Not a working day | understand the code | not a working day | not a working day
| Do you have any obstacles? | None | none | none | Nil | nil | nil | nil
Ethan | What did you do yesterday? | Read the wiki on the test casing | Going through the functionalities of boss | not a working day | pair coding with nanda | read wiki | read codes | not a working day
| What will you work on today? | going through the functionalities of boss | Not a working day | pair coding with nanda | read wiki | read codes | not a working day | not a working day
| Do you have any obstacles? | understanding the functionalities | Nil | nil | none | understanding | nil | nil
Yan Rui | What did you do yesterday? | Not a working day | Discuss iter 3 scheduling | not a working day | Go through round 2 clearing logic | not a working day | read code | not a working day
| What will you work on today? | Discuss iter 3 scheduling | Not a working day | go through round 2 clearing logic | Not a working day | read code | not a working day | not a working day
| Do you have any obstacles? | None | Nil | nil | Nil | nil | nil | nil
Haodi | What did you do yesterday? | consolidate test cases and further testing update on scheduling | deploy the application and submit project discuss about iter 3 scheduling | not working day | pari coding with SY for round 2 clearing logic | seek ways to improve ui | understand the code better | not a working day
| What will you work on today? | deploy the application and submit project discuss about iter 3 scheduling | Not a working day | pari coding with SY for round 2 clearing logic | seek ways to improve ui | understand the code better | not a working day | not a working day
| Do you have any obstacles? | None | Nil | nil | none | nil | none | nil

## Week 8
Person | Question | Week: 7/10/2019 - 13/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Nanda | What did you do yesterday? | Not a working day | Visit the wiki page to read updated information on PM related responsibilities | Pair coding with yanrui to code drop section functionality | Not a working day | Read the codes thus far | Not a working day | Group meeting to prepare for online demo
| What will you do today? | Visit the wiki page to read updated information on PM related responsibilities | Pair coding with yanrui to code drop section functionality | Not a working day | Read the codes thus far | Not a working day | Meeting to discuss about the online demo and prepare slides, as well as run some test cases | Not a working day
| Do you have any obstacles? | None | None | None | Understanding the functions called and the logic | None | None | None
Soo Yeon | What did you do yesterday? | Not a working day | holidays | holidays | holidays | read the codes that have been done so far | read the codes that have been done so far | Group meeting for online demo
| What will you work on today? | holidays | holidays | holidays | read the codes that have been done so far | read the codes that have been done so far | Group meeting for online demo | Not a working day
| Do you have any obstacles? | None | None | None | None | need to research some functions | None | None
Ethan | What did you do yesterday? | Not a working day | Not a working day | read through the codes | reread the requirements | Understanding the logic | Not a working day | pair coding with haodi, project meeting to discuss online demo
| What will you work on today? | Not a working day | Read through the codes | reread the requirements | Understanding the logic of codes | Not a working day | Pair coding with Haodi, project meeting to discuss online demo | read the wiki on the presentation tmr
| Do you have any obstacles? | None | Understanding the logic | finding out the requirments can be a bit tough | Tedious to read Logic online | None | coding | None
Yan Rui | What did you do yesterday? | Not a working day | Not a working day | pair coding with nanda | read up CSS for UI building | Not a working day | Read the codes | Group meeting for online demo
| What will you work on today? | Not a working day | Pair coding with Nanda | read up CSS for UI building | Not a working day | Read the codes | Group meeting for online demo | Not a working day
| Do you have any obstacles? | None | Nil | None | None | None | None | None
Haodi | What did you do yesterday? | Not a working day | condense redundant codes into functions to simply codes | Not a working day | read up round 1 clearing logic in wiki | Not a working day | Not a working day | Pair coding with ethan, project meeting for progress report
| What will you work on today? | review the codes so far and make amendments | Not a working day | read up round 1 clearing logic in wiki | Not a working day | Not a working day | Pair coding with ethan, project meeting for progress report | consolidate test cases and further testing update on scheduling
| Do you have any obstacles? | None | None | None | None | None | None | None

## Week 7
Person | Question | Week: 30/9/2019 to 6/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Nanda | What did you do yesterday? | Refer to PM Review Presentation Requirements and presentation slides | PM Review | Not a working day | Not a working day | Read Wiki page on updated requirements. | Revise week 1 and 2 slides | finish the incompleted tasks testing
| What will you do today? | PM Review | Not a working day | Not a working day | Read Wiki page on updated requirements. | Revise week 1 and 2 slides | finish the incompleted tasks testing | Not a working day
| Do you have any obstacles? | None | None | None | None | None | token error was a bit confusing | None
Soo Yeon | What did you do yesterday? | prepare for pm review | PM review | not a working day | pair coding with yanrui | not a working day | sick | finish the incompleted tasks testing
| What will you work on today? | pm review | not a working day | pair coding with yanrui | not a working day | sick | finish the incompleted tasks testing | Not a working day
| Do you have any obstacles? | none | none | need to revisit some concepts | none | none | Token error | None
Ethan | What did you do yesterday? | not a working day | pm review | reread the requirements | pair coding with haodi | reread through codes | pair coding with haodi | finish the incompleted tasks testing
| What will you work on today? | Review of the Project | reread the requirements | pair coding with haodi | reread through the codes | peer coding with haodi | finish the incompleted tasks testing | Not a working day
| Do you have any obstacles? | Learning what the other pair did | making sure it fits all the requirements | learning the concepts | none for now | none | confused about missing token error | None
Yan Rui | What did you do yesterday? | Pm review slides | pm review | not a working day | Pair coding with soo yeon | Not a working day | Review json concept | finish the incompleted tasks testing
| What will you work on today? | Pm review | not a working day | pair coding with Soo yeon | Not a working day | Review json concept | finish the incompleted tasks testing | Not a working day
| Do you have any obstacles? | Nil | nil | nil | Nil | Nil | Token errors. Token concept is confusing so had to go and revisit it and do some self research | None
Haodi | What did you do yesterday? | Test cases and Pm review meeting | PM review and team meeting for iter 2 | read the functionality requirement for tomorrow's pair coding | code dump table function with ethan | not a working day | pair coding with ethan to complete update bid in json and backend | finish the incompleted tasks testing
| What will you work on today? | PM review and team meeting for iter 2 | read the functionality requirement for tomorrow's pair coding | code dump table function with ethan | not a working day | pair coding with ethan to complete update bid and dump all tables | finish the incompleted tasks testing | Not a working day
| Do you have any obstacles? | confusion regarding authetication error msg | none | none | none | none | some confusion about missing token error | None

## Week 6
Person | Question | Week: 23/9/2019 to 29/9/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Nanda | What did you do yesterday? | Not a working day | Not a working day | Read wiki page for week 7 presentation requirements | Revise tokens and sessions (week 5 slides) | Do Project Management Quiz | Pair coding with Haodi | SPM Meeting
| What will you do today? | Not a working day | Read wiki page for week 7 presentation requirements | Revise tokens and sessions (week 5 slides) | Do Project Management Quiz | Pair coding with Haodi | SPM Meeting | Refer to PM Review Presentation Requirements and presentation slides
| Do you have any obstacles? | None | None | None | Retry the quiz a few times. Felt confused and revisited the slides. | None | None | None
Soo Yeon | What did you do yesterday? | not a working day | not a working day | revise tokens | complete quiz 3 | pair coding with haodi | not a working day | spm meeting
| What will you work on today? | not a working day | revise tokens | complete quiz 3 | pair coding with haodi | not a working day | spm meeting | prepare for pm review tomorrow
| Do you have any obstacles? | none | had to do extra self-study for better understanding | none | none | none | having to read through the schedule requirements more thoroughly | none
Ethan | What did you do yesterday? | Not a working day | Read the requirements | Did PM quiz | pair coding with yan rui | not a working day | revise sessions | spm meeting
| What will you work on today? | Read the wiki requirements | learn on project management by doing the quiz | Pair coding with Yan Rui | not a working day | revise sessions | spm meeting | not a working day
| Do you have any obstacles? | Too many requirements, have to plan the schedule properly | Yes it's too difficult | We had to change our meeting time due to unforseen circumstances | none | weak grasp of linking pages tgt | none | none
Yan Rui | What did you do yesterday? | Not a working day | Go thru spm refresher | Read wiki requirements | Pair coding with Ethan | Complete quiz 3 | not a working day | Spm meeting
| What will you work on today? | Go through spm refresher | Read wiki requirements | Pair coding with Ethan | Complete quiz 3 | not a working day | spm meeting | PM review slides
| Do you have any obstacles? | Nil | A lot of requirements | Nil | Nil | Nil | nil | nil
Haodi | What did you do yesterday? | not a working day | read the pm review and deploy the current app onto aws | not a working day | check the PM review requirement with the new slides sent by prof | pair coding with SY | finish bootstrap function but with some bugs | debug bootstrap and spm meeting
| What will you work on today? | read the updated PM review requirement | not a working day | check the PM review requirement with the new slides sent by prof | pair coding with SY | pair coding with Nanda | debug bootstrap and spm meeting | PM Review slides and draw critical path
| Do you have any obstacles? | none | none | none | None | None | no | some confusion regarding critical path

## Week 5
Person | Question | Week: 16/9/2019 to 22/9/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Nanda | What did you do yesterday? | not a working day | Come up with a team schedule for the project | Updated myself with the new requirements on the wiki page and broke down the new information. | Sick | Revised JSON and GIT, and in-class labs. | Do the Insert value SQL script Pair coding with Haodi. | Revised PHP concepts (DAO, PDO, Database Interaction)
| What will you do today? | Come up with a team schedule for the project | Read the updated wiki page | Sick | Did some research on how JSON and GIT works, and relooked at the past labs done in class. | Do the Insert value SQL script Pair coding with Haodi. | Revised PHP concepts (DAO, PDO, Database Interaction) | not a working day
| Do you have any obstacles? | Some members were not able to attend on certain days, so we had to make adjustments to find a common time for everyone. | None | None | Had to do a lot of self-research since the lab does not explain the workings of JSON and GIT in depth. | None | None | None
Soo Yeon | What did you do yesterday? | Create the SQL scripts to create database for the project | researched and read about bootstrap | read about bootstrap | ended up reading and revising sql | revisit php | attend SPM refresher class | re-attempt exercises from SPM refresher class
| What will you do today? | Researched and read about bootstrap | read about bootstrap | create sql script | revisit php | attend SPM refresher class | re-attempt exercises from SPM refresher class | not a working day
| Do you have any obstacles? | the export setting in the phpmyadmin is different from what is described in the wiki. TA has clarified the difference | none | none | finding time to revise these with many things to do | none | still had to refer to preivous exercises i did last sem | none
Ethan | What did you do yesterday? | not a working day | Managed to schedule my timing to meet my Pair for coding as well as set a team meeting together | Managed to Understand classes a lot better than before | Pair coding with Yan Rui | Couldn't really learn much of session Etc will get help from my group members asap | attend spm refresher class | Test Cases
| What will you work on today? | Discuss team scheduling with Yan Rui. Find out the best timing to meet | Revised PHP | Pair coding with Yan Rui | Try to understand PHP in terms of Session Etc. | Going for a SPM refresher course | Group meeting with test cases | not a working day
| Do you have any obstacles? | We had difficult coming with a common timeslot but we eventually decided on a morning slot to meet up | I have a weak foundation in PHP so it takes me a while to get use to the syntax | Waking up early for the meeting | It is difficult when no one is guiding me because everything has to be found online | None for now | Getting a time for us to meet and there are some bugs here and there which we need to resolve | none
Yan Rui | What did you do yesterday? | not a working day | Finding a common timeslot with Ethan | Revised PHP | Created several objects and classes via pair coding with Ethan | revisited PHP concepts on login and authenticate | work on and complete in class labs exercise | testing our codes
| What will you work on today? | Discuss team scheduling with Ethan. Find out the best timing to meet | Revised PHP | Creating objects and classes via pair coding with Ethan | Revisit PHP | work on and complete the labs | testing our codes | not a working day
| Do you have any obstacles? | We had difficulty finding a common timeslot due to our conflicting schedules but we managed to find one in the end | Yes, it took me some time to recall and revise what I've learnt before | Waking up early for the meeting | Need to schedule time for revision. | nil | nil | none
Haodi | What did you do yesterday? | Read the updated wiki | Create the SQL scripts to create database tables for the project Discuss scheduling with team mates | not a working day | Draw critical path of current scheduling | Tried out some logic validations | Do the Insert value SQL script Pair coding with Nanda | testing current codes and update schedules
| What will you work on today? | Create the SQL scripts to create database tables for the project Discuss scheduling with team mates | not a working day | Code out DAO classes | Try out validation with data in the database | Do the Insert value SQL script Pair coding with Nanda | Week 5 meeting testing current codes | not a working day
| Do you have any obstacles? | None | The export setting in the phpmyadmin is different from what is described in the wiki. TA has clarified the difference. | None | None | None | Very busy as I had a midterm and CCA meeting before SPM meeting | none